## Tracking Remarks
2017-09-01
Key reasons for delay:
1. Lack of Design document upfront. Developers had to create the design, effort for which was not included in the estimates
2. Solution approach changed due to design created by developers while carrying out development
3. Inadequate knowledge of TeamPatent application code
4. Some user stories were more complex than what was originally anticipated
5. Variance in the original estimates because effort estimation was carried out without any wireframes provided. Was based only on the basis of user story acceptance criteria.
6. Application business logic and workflow are not very clear due to lack of any system documentation
S. No. | EPIC Name | User Story Title | Remarks Received on | Tracking Remarks | Impacted Area's | Impact in Mandays
1 | CR3-1&2 | All | 2018-01-05 | 2 days delay due to complex defects and bug fixing of release 4.0 | Release 4.1 | 9
2 | CR3-1&2 | All | 2018-01-12 | Unlanned deployment effort | Release 4.1 | 11.5
3 | CR3-1&2 | All | 19/01/2018 | Delayed in 1 US due to its complexity | Release 4.1 | 5
4 | Functional Improvements and NFRs | 3530, 4033 ans 5199 | 2018-02-02 | Response delay from BI and FO UI has delayed the progress 1 security US has been added on request | Release 4.1 | 6
5 | Functional Improvements | 3530 and 3959 | 2018-02-09 | Need to incorporate changes at BI and MUSE end | Release 4.1 | 3

## Release 4.1
Date | 2018-01-05 | 2018-01-12 | 2018-01-19 | 2018-01-26 | 2018-02-02 | 2018-02-09
Original Budget (BAC) | 1672.5 | 1664.5 | 1664.5 | 1664.5 | 1664.5 | 1664.5
Change control days (if any) | 0 | 0 | 0 | 0 | 0 | 0
Revised Budget (RBAC) | 0 | 0 | 0 | 0 | 0 | 0
Actuals (AC) | 1770 | 1821 | 1882 | 1937 | 2000 | 2028
Estimate to Complete (ETC) | 240.5 | 179.8 | 121 | 66 | 9 | 2.5
Estimate at Completion (EAC) | 2010.5 | 2000.8 | 2003 | 2003 | 2009 | 2030.5
Productivity % | 83.19% | 83.19% | 83.1% | 83.1% | 82.85% | 81.97%
%age completed against EAC | 88.04% | 91.01% | 93.96% | 96.7% | 99.55% | 99.88%
CR3-Combined | 2018-01-05 | 2018-01-12 | 2018-01-19 | 2018-01-26 | 2018-02-02 | 2018-02-09
Planned progress | 90 | 91 | 96 | 98 | 100 | 100
Actual progress | 88.0378 | 91.0136 | 93.9591 | 96.7049 | 99.552 | 99.8769
Note on W3: Revised to remove Setting user story EDOS-3728
Note on C15: 2 days delay due to complex bugs and bug fixing of release 4.0
Note on E15: Delay due to complexity of image user story
Note on G15: Response delay from BI and FO UI has delayed the progress 1 security US has been added on request
Note on H15: Need to incorporate changes done at BI and MUSE end
Note on Y15: High number System testing defects raised. Resolution is in progress.

## Tracker-09Feb
EPIC | No. of User Stories | US S. No. | User Story Title |  |  |  | Efforts in mandays (Dev+UT+ST) | [7 empty] | Delivery Date |  | Status | Comments | Assigned to
|  |  |  | US/CR Approved On | Latest Wireframe Available On | Latest Design Document Available On | Original Budget (BAC) | Actuals (As on Date) (AC) | Percentage Completed (%) | Earned Value (EV) | Cost Performance Index (CPI) | Estimate at Completion (EAC) | Estimate to Complete (ETC) | Productivity | Original | Revised*
CR3-1&2 | 30 | 1 | CR3-1&2 | In 2017 | In 2017 | N/A | 1178 | 1541 | 100 | 1178 | 0.76444 | 1541 | 0 | 76.44% | 2017-12-01 | 2018-01-19 | Completed
| 6 | 1 | CR3-1&2 Remaining 6 User Stories | In 2017 | In 2017 | N/A | 250 | 240 | 99 | 247.5 | 1.0312 | 240.5 | 0.5 | 104% | 2017-12-01 | 2018-01-19 | 1 ST Defect pending
CR3 Part3 | 3 | 1 | EDOS-4247 - Open Helper module | 2017-12-01 | 2017-12-01 | N/A | 37.5 | 39 | 100 | 37.5 | 0.96154 | 39 | 0 | 96.15% | 2018-02-02 |  | Completed
|  | 2 | EDOS-4248 - See a helper in Helpers module | 2017-12-01 | 2017-12-01 | N/A | 37.5 | 40 | 100 | 37.5 | 0.9375 | 40 | 0 | 93.75% | 2018-02-02 |  | Completed
|  | 3 | EDOS-4249 - Move and Rezise helpers in Helpers module | 2017-12-01 | 2017-12-01 | N/A | 12.5 | 13 | 100 | 12.5 | 0.96154 | 13 | 0 | 96.15% | 2018-02-02 |  | Completed
Changes in VIN Bar | 5 | 1 | Changes in VIN Bar | 2018-10-26 | 2018-10-26 | N/A | 50 | 50 | 100 | 50 | 1 | 50 | 0 | 100% | 2018-02-02 |  | Completed
Functional improvements | 5 | 1 | EDOS-3959 - All list of names should be sorted by Last Name | 2017-11-07 | 2017-11-07 | N/A | 23 | 25 | 99 | 22.77 | 0.9108 | 26 | 1 | 88.46% | 2018-02-02 |  | There are changes at BI end . Those changes have to be incorporate in TeamPatent
|  | 2 | EDOS-3484 - Autocomplete in search division | 2017-11-07 | 2017-11-07 | N/A | 20 | 22 | 100 | 20 | 0.90909 | 22 | 0 | 90.91% | 2018-02-02 |  | Completed
|  | 3 | EDOS-3530 - Proposed first examiner Snippets visual reference | 2017-11-07 | 2017-11-07 | N/A | 17 | 17 | 99 | 16.83 | 0.99 | 18 | 1 | 94.44% | 2018-02-02 |  | There are changes at BI and MUSE end . Those changes have to be incorporate in TeamPatent
|  | 4 | EDOS-4033 - Default values for Secondary actions on the snippet preview | 2017-11-17 | 2017-11-17 | N/A | 6 | 8 | 100 | 6 | 0.75 | 8 | 0 | 75% | 2018-02-02 |  | Completed
|  | 5 | EDOS-4801 - Tooltip for Associated Fillings and Number Indicator | 2017-11-14 | 2017-11-14 | N/A | 10 | 10 | 100 | 10 | 1 | 10 | 0 | 100% | 2018-02-02 |  | Completed
NFRs | 5 | 1 | EDOS-5199 | 2018-01-09 | 2018-01-09 | N/A | 7 | 7 | 100 | 7 | 1 | 7 | 0 | 100% | 2018-02-02 |  | Completed
|  | 2 | EDOS-5202 | 2018-01-09 | 2018-01-09 | N/A | 7 | 7 | 100 | 7 | 1 | 7 | 0 | 100% | 2018-02-02 |  | Completed
|  | 3 | EDOS-5208 | 2018-01-09 | 2018-01-09 | N/A | 4 | 4 | 100 | 4 | 1 | 4 | 0 | 100% | 2018-02-02 |  | Completed
On request from release 4.0 |  | 1 | EDOS-4852 | In 2017 | In 2017 | N/A | 2 | 2 | 100 | 2 | 1 | 2 | 0 | 100% | 2018-02-02 |  | Completed
|  | 2 | EDOS-4854 | In 2017 | In 2017 | N/A | 3 | 3 | 100 | 3 | 1 | 3 | 0 | 100% | 2018-02-02 |  | Completed
|  |  | Total |  |  |  | 1664.5 | 2028 | 99.8125 | 1661.3791 | 0.81922 | 2030.5 | 2.5 | 81.97%
99.88%
[7 empty] | 1664.5 | 2028 | 99.8125 | #REF! | #REF! | 2030.5 | 2.5
SIT Support |  |  | All | N/A | N/A | N/A | 96 | 39 | 18 |  |  | 117 | 78 | 82.05% | 2018-02-28 |  | In progress
AOT |  |  | AOT | N/A | N/A | N/A | 17 | 9 | 30 |  |  | 17 | 8 | 100% | 2018-02-28 |  | In progress
Deployement |  |  | All | N/A | N/A | N/A | 0 | 15 | 100 | 0 | 0 | 15 | 0 | 0% | 2018-02-28 |  | In progress
|  |  | Total |  |  |  | 113 | 63 | 49.3333 | 55.7467 | 0.88487 | 149 | 86 | 75.84%

## Tracker-02Feb
EPIC | No. of User Stories | US S. No. | User Story Title |  |  |  | Efforts in mandays (Dev+UT+ST) | [7 empty] | Delivery Date |  | Status | Comments | Assigned to
|  |  |  | US/CR Approved On | Latest Wireframe Available On | Latest Design Document Available On | Original Budget (BAC) | Actuals (As on Date) (AC) | Percentage Completed (%) | Earned Value (EV) | Cost Performance Index (CPI) | Estimate at Completion (EAC) | Estimate to Complete (ETC) | Productivity | Original | Revised*
CR3-1&2 | 30 | 1 | CR3-1&2 | In 2017 | In 2017 | N/A | 1178 | 1536 | 100 | 1178 | 0.76693 | 1536 | 0 | 76.69% | 2017-12-01 | 2018-01-19 | Completed
| 6 | 1 | CR3-1&2 Remaining 6 User Stories | In 2017 | In 2017 | N/A | 250 | 237 | 99 | 247.5 | 1.0443 | 237 | 0 | 105.5% | 2017-12-01 | 2018-01-19 | ST inprogress
CR3 Part3 | 3 | 1 | EDOS-4247 - Open Helper module | 2017-12-01 | 2017-12-01 | N/A | 37.5 | 37 | 100 | 37.5 | 1.0135 | 37 | 0 | 101.4% | 2018-02-02 |  | Completed
|  | 2 | EDOS-4248 - See a helper in Helpers module | 2017-12-01 | 2017-12-01 | N/A | 37.5 | 37 | 100 | 37.5 | 1.0135 | 37 | 0 | 101.4% | 2018-02-02 |  | Completed
|  | 3 | EDOS-4249 - Move and Rezise helpers in Helpers module | 2017-12-01 | 2017-12-01 | N/A | 12.5 | 13 | 100 | 12.5 | 0.96154 | 13 | 0 | 96.15% | 2018-02-02 |  | Completed
Changes in VIN Bar | 5 | 1 | Changes in VIN Bar | 2018-10-26 | 2018-10-26 | N/A | 50 | 50 | 100 | 50 | 1 | 50 | 0 | 100% | 2018-02-02 |  | Completed
Functional improvements | 5 | 1 | EDOS-3959 - All list of names should be sorted by Last Name | 2017-11-07 | 2017-11-07 | N/A | 23 | 23 | 100 | 23 | 1 | 23 | 0 | 100% | 2018-02-02 |  | Completed
|  | 2 | EDOS-3484 - Autocomplete in search division | 2017-11-07 | 2017-11-07 | N/A | 20 | 20 | 100 | 20 | 1 | 20 | 0 | 100% | 2018-02-02 |  | Completed
|  | 3 | EDOS-3530 - Proposed first examiner Snippets visual reference | 2017-11-07 | 2017-11-07 | N/A | 17 | 14 | 80 | 13.6 | 0.97143 | 17 | 3 | 100% | 2018-02-02 |  | In progress
|  | 4 | EDOS-4033 - Default values for Secondary actions on the snippet preview | 2017-11-17 | 2017-11-17 | N/A | 6 | 3 | 80 | 4.8 | 1.6 | 6 | 3 | 100% | 2018-02-02 |  | In progress
|  | 5 | EDOS-4801 - Tooltip for Associated Fillings and Number Indicator | 2017-11-14 | 2017-11-14 | N/A | 10 | 10 | 100 | 10 | 1 | 10 | 0 | 100% | 2018-02-02 |  | Completed
NFRs | 5 | 1 | EDOS-5199 | 2018-01-09 | 2018-01-09 | N/A | 7 | 4 | 60 | 4.2 | 1.05 | 7 | 3 | 100% | 2018-02-02 |  | In progress
|  | 2 | EDOS-5202 | 2018-01-09 | 2018-01-09 | N/A | 7 | 7 | 100 | 7 | 1 | 7 | 0 | 100% | 2018-02-02 |  | Completed
|  | 3 | EDOS-5208 | 2018-01-09 | 2018-01-09 | N/A | 4 | 4 | 100 | 4 | 1 | 4 | 0 | 100% | 2018-02-02 |  | Completed
On request from release 4.0 |  | 1 | EDOS-4852 | In 2017 | In 2017 | N/A | 2 | 2 | 100 | 2 | 1 | 2 | 0 | 100% | 2018-02-02 |  | Completed
|  | 2 | EDOS-4854 | In 2017 | In 2017 | N/A | 3 | 3 | 100 | 3 | 1 | 3 | 0 | 100% | 2018-02-02 |  | Completed
|  |  | Total |  |  |  | 1664.5 | 2000 | 94.9375 | 1580.2347 | 0.79012 | 2009 | 9 | 82.85%
99.55%
[7 empty] | 1664.5 | 2000 | 94.9375 | #REF! | #REF! | 2009 | 9
SIT Support |  |  | All | N/A | N/A | N/A | 96 | 18 | 18 |  |  | 96 | 78 | 100% | 2018-02-03 |  | In progress
AOT |  |  | AOT | N/A | N/A | N/A | 17 | 9 | 30 |  |  | 17 | 8 | 100% | 2018-02-03 |  | In progress
|  |  | Total |  |  |  | 113 | 27 | 24 | 27.12 | 1.0044 | 113 | 86 | 100%

## Tracker-26Jan
EPIC | No. of User Stories | US S. No. | User Story Title |  |  |  | Efforts in mandays (Dev+UT+ST) | [7 empty] | Delivery Date |  | Status | Comments | Assigned to
|  |  |  | US/CR Approved On | Latest Wireframe Available On | Latest Design Document Available On | Original Budget (BAC) | Actuals (As on Date) (AC) | Percentage Completed (%) | Earned Value (EV) | Cost Performance Index (CPI) | Estimate at Completion (EAC) | Estimate to Complete (ETC) | Productivity | Original | Revised*
CR3-1&2 | 30 | 1 | CR3-1&2 | In 2017 | In 2017 | N/A | 1178 | 1535 | 100 | 1178 | 0.76743 | 1535 | 0 | 76.74% | 2017-12-01 | 2018-01-19 | All system testing defects resolved. 2 defects retest pending
| 6 | 1 | CR3-1&2 Remaining 6 User Stories | In 2017 | In 2017 | N/A | 250 | 229 | 94 | 235 | 1.0262 | 232 | 3 | 107.8% | 2017-12-01 | 2018-01-19 | 1 user story ST completed. 3 User Stories in ST. 2 User stories in progress.
CR3 Part3 | 3 | 1 | EDOS-4247 - Open Helper module | 2017-12-01 | 2017-12-01 | N/A | 37.5 | 25 | 80 | 30 | 1.2 | 37 | 12 | 101.4% | 2018-02-02 |  | ST In progress
|  | 2 | EDOS-4248 - See a helper in Helpers module | 2017-12-01 | 2017-12-01 | N/A | 37.5 | 25 | 80 | 30 | 1.2 | 37 | 12 | 101.4% | 2018-02-02 |  | ST In progress
|  | 3 | EDOS-4249 - Move and Rezise helpers in Helpers module | 2017-12-01 | 2017-12-01 | N/A | 12.5 | 11 | 80 | 10 | 0.90909 | 13 | 2 | 96.15% | 2018-02-02 |  | ST In progress
Changes in VIN Bar | 5 | 1 | Changes in VIN Bar | 2018-10-26 | 2018-10-26 | N/A | 50 | 41 | 80 | 40 | 0.97561 | 50 | 9 | 100% | 2018-02-02 |  | ST In progress
Functional improvements | 5 | 1 | EDOS-3959 - All list of names should be sorted by Last Name | 2017-11-07 | 2017-11-07 | N/A | 23 | 13 | 60 | 13.8 | 1.0615 | 23 | 10 | 100% | 2018-02-02 |  | In progress
|  | 2 | EDOS-3484 - Autocomplete in search division | 2017-11-07 | 2017-11-07 | N/A | 20 | 18 | 80 | 16 | 0.88889 | 20 | 2 | 100% | 2018-02-02 |  | ST In progress
|  | 3 | EDOS-3530 - Proposed first examiner Snippets visual reference | 2017-11-07 | 2017-11-07 | N/A | 17 | 14 | 70 | 11.9 | 0.85 | 17 | 3 | 100% | 2018-02-02 |  | Ready for ST
|  | 4 | EDOS-4033 - Default values for Secondary actions on the snippet preview | 2017-11-17 | 2017-11-17 | N/A | 6 | 3 | 70 | 4.2 | 1.4 | 6 | 3 | 100% | 2018-02-02 |  | Ready for ST
|  | 5 | EDOS-4801 - Tooltip for Associated Fillings and Number Indicator | 2017-11-14 | 2017-11-14 | N/A | 10 | 10 | 100 | 10 | 1 | 10 | 0 | 100% | 2018-02-02 |  | Completed
NFRs | 5 | 1 | EDOS-5199 | 2018-01-09 | 2018-01-09 | N/A | 7 | 1 | 30 | 2.1 | 2.1 | 7 | 6 | 100% | 2018-02-02 |  | In progress
|  | 2 | EDOS-5202 | 2018-01-09 | 2018-01-09 | N/A | 7 | 5 | 80 | 5.6 | 1.12 | 7 | 2 | 100% | 2018-02-02 |  | ST In progress
|  | 3 | EDOS-5208 | 2018-01-09 | 2018-01-09 | N/A | 4 | 2 | 90 | 3.6 | 1.8 | 4 | 2 | 100% | 2018-02-02 |  | ST In progress
On request from release 4.0 |  | 1 | EDOS-4852 | In 2017 | In 2017 | N/A | 2 | 2 | 100 | 2 | 1 | 2 | 0 | 100% | 2018-02-02 |  | Completed
|  | 2 | EDOS-4854 | In 2017 | In 2017 | N/A | 3 | 3 | 100 | 3 | 1 | 3 | 0 | 100% | 2018-02-02 |  | Completed
|  |  | Total |  |  |  | 1664.5 | 1937 | 80.875 | 1346.1644 | 0.69497 | 2003 | 66 | 83.1%
96.7%
[7 empty] | 1664.5 | 1937 | 80.875 | #REF! | #REF! | 2003 | 66

## Tracker-19Jan
EPIC | No. of User Stories | US S. No. | User Story Title |  |  |  | Efforts in mandays (Dev+UT+ST) | [7 empty] | Delivery Date |  | Status | Comments | Assigned to
|  |  |  | US/CR Approved On | Latest Wireframe Available On | Latest Design Document Available On | Original Budget (BAC) | Actuals (As on Date) (AC) | Percentage Completed (%) | Earned Value (EV) | Cost Performance Index (CPI) | Estimate at Completion (EAC) | Estimate to Complete (ETC) | Productivity | Original | Revised*
CR3-1&2 | 30 | 1 | CR3-1&2 | In 2017 | In 2017 | N/A | 1178 | 1535 | 100 | 1178 | 0.76743 | 1535 | 0 | 76.74% | 2017-12-01 | 2018-01-19 | All system testing defects resolved. 2 defects will be resolved with VIN Bar changes
| 6 | 1 | CR3-1&2 Remaining 6 User Stories | In 2017 | In 2017 | N/A | 250 | 227 | 90 | 225 | 0.99119 | 232 | 5 | 107.8% | 2017-12-01 | 2018-01-19 | 1 user story ST completed. 3 User Stories in ST. 2 User stories in completed.
CR3 Part3 | 3 | 1 | EDOS-4247 - Open Helper module | 2017-12-01 | 2017-12-01 | N/A | 37.5 | 16 | 50 | 18.75 | 1.1719 | 37 | 21 | 101.4% | 2018-02-02 |  | In progress
|  | 2 | EDOS-4248 - See a helper in Helpers module | 2017-12-01 | 2017-12-01 | N/A | 37.5 | 16 | 50 | 18.75 | 1.1719 | 38 | 22 | 98.68% | 2018-02-02 |  | In progress
|  | 3 | EDOS-4249 - Move and Rezise helpers in Helpers module | 2017-12-01 | 2017-12-01 | N/A | 12.5 | 8 | 50 | 6.25 | 0.78125 | 13 | 5 | 96.15% | 2018-02-02 |  | In progress
Changes in VIN Bar | 5 | 1 | Changes in VIN Bar | 2018-10-26 | 2018-10-26 | N/A | 50 | 29 | 60 | 30 | 1.0345 | 50 | 21 | 100% | 2018-02-02 |  | In progress
Functional improvements | 5 | 1 | EDOS-3959 - All list of names should be sorted by Last Name | 2017-11-07 | 2017-11-07 | N/A | 23 | 10 | 20 | 4.6 | 0.46 | 23 | 13 | 100% | 2018-02-02 |  | In progress
|  | 2 | EDOS-3484 - Autocomplete in search division | 2017-11-07 | 2017-11-07 | N/A | 20 | 18 | 70 | 14 | 0.77778 | 20 | 2 | 100% | 2018-02-02 |  | Ready for ST
|  | 3 | EDOS-3530 - Proposed first examiner Snippets visual reference | 2017-11-07 | 2017-11-07 | N/A | 17 | 7 | 20 | 3.4 | 0.48571 | 15 | 8 | 113.3% | 2018-02-02 |  | In progress
|  | 4 | EDOS-4033 - Default values for Secondary actions on the snippet preview | 2017-11-17 | 2017-11-17 | N/A | 6 | 1 | 10 | 0.6 | 0.6 | 6 | 5 | 100% | 2018-02-02 |  | In progress
|  | 5 | EDOS-4801 - Tooltip for Associated Fillings and Number Indicator | 2017-11-14 | 2017-11-14 | N/A | 10 | 5 | 95 | 9.5 | 1.9 | 10 | 5 | 100% | 2018-02-02 |  | System Testing in progress
NFRs | 5 | 1 | EDOS-5199 | 2018-01-09 | 2018-01-09 | N/A | 7 |  | 0 | 0 | #DIV/0! | 7 | 7 | 100% | 2018-02-02 |  | In progress
|  | 2 | EDOS-5202 | 2018-01-09 | 2018-01-09 | N/A | 7 | 3 | 70 | 4.9 | 1.6333 | 8 | 5 | 87.5% | 2018-02-02 |  | Ready for ST
|  | 3 | EDOS-5208 | 2018-01-09 | 2018-01-09 | N/A | 4 | 2 | 70 | 2.8 | 1.4 | 4 | 2 | 100% | 2018-02-02 |  | Ready for ST
On request from release 4.0 |  | 1 | EDOS-4852 | In 2017 | In 2017 | N/A | 2 | 2 | 100 | 2 | 1 | 2 | 0 | 100% | 2018-02-02 |  | Completed
|  | 2 | EDOS-4854 | In 2017 | In 2017 | N/A | 3 | 3 | 100 | 3 | 1 | 3 | 0 | 100% | 2018-02-02 |  | Completed
|  |  | Total |  |  |  | 1664.5 | 1882 | 59.6875 | 993.4984 | 0.5279 | 2003 | 121 | 83.1%
93.96%
[7 empty] | 1664.5 | 1882 | 59.6875 | #REF! | #REF! | 2003 | 121

## Tracker-12Jan
EPIC | No. of User Stories | US S. No. | User Story Title |  |  |  | Efforts in mandays (Dev+UT+ST) | [7 empty] | Delivery Date |  | Status | Comments | Assigned to
|  |  |  | US/CR Approved On | Latest Wireframe Available On | Latest Design Document Available On | Original Budget (BAC) | Actuals (As on Date) (AC) | Percentage Completed (%) | Earned Value (EV) | Cost Performance Index (CPI) | Estimate at Completion (EAC) | Estimate to Complete (ETC) | Productivity | Original | Revised*
CR3-1&2 | 30 | 1 | CR3-1&2 | In 2017 | In 2017 | N/A | 1178 | 1534 | 100 | 1178 | 0.76793 | 1534 | 0 | 76.79% | 2017-12-01 | 2018-01-19 | All system testing defects resolved. 2 defects will be resolved with VIN Bar changes
| 6 | 1 | CR3-1&2 Remaining 6 User Stories | In 2017 | In 2017 | N/A | 250 | 222 | 90 | 225 | 1.0135 | 230 | 8 | 108.7% | 2017-12-01 | 2018-01-19 | On user story in ST. 2 development completed and 3 inprogress
CR3 Part3 | 3 | 1 | EDOS-4247 - Open Helper module | 2017-12-01 | 2017-12-01 | N/A | 37.5 | 9 | 20 | 7.5 | 0.83333 | 37.8 | 28.8 | 99.21% | 2018-02-02 |  | In progress
|  | 2 | EDOS-4248 - See a helper in Helpers module | 2017-12-01 | 2017-12-01 | N/A | 37.5 | 9 | 20 | 7.5 | 0.83333 | 37.5 | 28.5 | 100% | 2018-02-02 |  | In progress
|  | 3 | EDOS-4249 - Move and Rezise helpers in Helpers module | 2017-12-01 | 2017-12-01 | N/A | 12.5 | 6 | 20 | 2.5 | 0.41667 | 12.5 | 6.5 | 100% | 2018-02-02 |  | In progress
Changes in VIN Bar | 5 | 1 | Changes in VIN Bar | 2018-10-26 | 2018-10-26 | N/A | 50 | 17 | 2 | 1 | 0.058824 | 50 | 33 | 100% | 2018-02-02 |  | In progress
Functional improvements | 5 | 1 | EDOS-3959 - All list of names should be sorted by Last Name | 2017-11-07 | Not Approved | N/A | 23 | 3 | 5 | 1.15 | 0.38333 | 23 | 20 | 100% | 2018-02-02 |  | In progress
|  | 2 | EDOS-3484 - Autocomplete in search division | 2017-11-07 | Not Approved | N/A | 20 | 12 | 2 | 0.4 | 0.033333 | 20 | 8 | 100% | 2018-02-02 |  | In progress
|  | 3 | EDOS-3530 - Proposed first examiner Snippets visual reference | 2017-11-07 | Not Approved | N/A | 17 | 7 | 2 | 0.34 | 0.048571 | 15 | 8 | 113.3% | 2018-02-02 |  | In progress
|  | 4 | EDOS-4033 - Default values for Secondary actions on the snippet preview | 2017-11-17 | Not Approved | N/A | 6 | 1 | 0 | 0 | 0 | 6 | 5 | 100% | 2018-02-02 |  | In progress
|  | 5 | EDOS-4801 - Tooltip for Associated Fillings and Number Indicator | 2017-11-14 | Not Approved | N/A | 10 | 1 | 5 | 0.5 | 0.5 | 11 | 10 | 90.91% | 2018-02-02 |  | System Testing in progress
NFRs | 5 | 1 | EDOS-5199 | 2018-01-09 | 2018-01-09 | N/A | 7 |  | 0 | 0 | #DIV/0! | 7 | 7 | 100% | 2018-02-02
|  | 2 | EDOS-5202 | 2018-01-09 | 2018-01-09 | N/A | 7 |  | 0 | 0 | #DIV/0! | 8 | 8 | 87.5% | 2018-02-02
|  | 3 | EDOS-5208 | 2018-01-09 | 2018-01-09 | N/A | 4 |  | 0 | 0 | #DIV/0! | 4 | 4 | 100% | 2018-02-02
On request from release 4.0 |  | 1 | EDOS-4852 | In 2017 | In 2017 | N/A | 2 |  | 0 | 0 | #DIV/0! | 2 | 2 | 100% | 2018-02-02 |  | System Testing in progress
|  | 2 | EDOS-4854 | In 2017 | In 2017 | N/A | 3 |  | 0 | 0 | #DIV/0! | 3 | 3 | 100% | 2018-02-02 |  | System Testing in progress
|  |  | Total |  |  |  | 1664.5 | 1821 | 16.625 | 276.7231 | 0.15196 | 2000.8 | 179.8 | 83.19%
91.01%
[7 empty] | 1664.5 | 1821 | 16.625 | #REF! | #REF! | 2000.8 | 179.8

## Tracker-05Jan
EPIC | No. of User Stories | US S. No. | User Story Title |  |  |  | Efforts in mandays (Dev+UT+ST) | [7 empty] | Delivery Date |  | Status | Comments | Assigned to
|  |  |  | US/CR Approved On | Latest Wireframe Available On | Latest Design Document Available On | Original Budget (BAC) | Actuals (As on Date) (AC) | Percentage Completed (%) | Earned Value (EV) | Cost Performance Index (CPI) | Estimate at Completion (EAC) | Estimate to Complete (ETC) | Productivity | Original | Revised*
CR3-1&2 | 30 | 1 | CR3-1&2 | In 2017 | In 2017 | N/A | 1178 | 1533 | 99 | 1166.22 | 0.76074 | 1534 | 1 | 76.79% | 2017-12-01 | 2018-01-05
| 6 | 1 | CR3-1&2 Remaining 6 User Stories | In 2017 | In 2017 | N/A | 250 | 220 | 90 | 225 | 1.0227 | 231 | 11 | 108.2% | 2017-12-01 | 2018-01-05
CR3 Part3 | 3 | 1 | EDOS-4247 - Open Helper module | 2017-12-01 | 2017-12-01 | N/A | 37.5 | 2.5 | 5 | 1.875 | 0.75 | 37.5 | 35 | 100% | 2018-02-02
|  | 2 | EDOS-4248 - See a helper in Helpers module | 2017-12-01 | 2017-12-01 | N/A | 37.5 | 2.5 | 5 | 1.875 | 0.75 | 37.5 | 35 | 100% | 2018-02-02
|  | 3 | EDOS-4249 - Move and Rezise helpers in Helpers module | 2017-12-01 | 2017-12-01 | N/A | 12.5 | 1 | 2 | 0.25 | 0.25 | 12.5 | 11.5 | 100% | 2018-02-02
Changes in VIN Bar | 5 | 1 | Changes in VIN Bar | 2018-10-26 | 2018-10-26 | N/A | 50 | 4 | 2 | 1 | 0.25 | 50 | 46 | 100% | 2018-02-02
Functional improvements | 5 | 1 | EDOS-3959 - All list of names should be sorted by Last Name | Not Approved | Not Approved | N/A | 23 | 3 | 5 | 1.15 | 0.38333 | 23 | 20 | 100% | 2018-02-02
|  | 2 | EDOS-3484 - Autocomplete in search division | Not Approved | Not Approved | N/A | 20 | 2 | 2 | 0.4 | 0.2 | 20 | 18 | 100% | 2018-02-02
|  | 3 | EDOS-3530 - Proposed first examiner Snippets visual reference | Not Approved | Not Approved | N/A | 17 | 1 | 2 | 0.34 | 0.34 | 17 | 16 | 100% | 2018-02-02
|  | 4 | EDOS-4033 - Default values for Secondary actions on the snippet preview | Not Approved | Not Approved | N/A | 6 |  | 0 | 0 | #DIV/0! | 6 | 6 | 100% | 2018-02-02
|  | 5 | EDOS-4801 - Tooltip for Associated Fillings and Number Indicator | Not Approved | Not Approved | N/A | 10 | 1 | 5 | 0.5 | 0.5 | 11 | 10 | 90.91% | 2018-02-02
NFRs | 5 | 1 | EDOS-5199 | Not Approved | Not Approved | N/A | 7 |  | 0 | 0 | #DIV/0! | 7 | 7 | 100% | 2018-02-02
|  | 2 | EDOS-5202 | Not Approved | Not Approved | N/A | 8 |  | 0 | 0 | #DIV/0! | 8 | 8 | 100% | 2018-02-02
|  | 3 | EDOS-5203 | Not Approved | Not Approved | N/A | 6 |  | 0 | 0 | #DIV/0! | 6 | 6 | 100% | 2018-02-02
|  | 4 | EDOS-5204 | Not Approved | Not Approved | N/A | 6 |  | 0 | 0 | #DIV/0! | 6 | 6 | 100% | 2018-02-02
|  | 5 | EDOS-5208 | Not Approved | Not Approved | N/A | 4 |  | 0 | 0 | #DIV/0! | 4 | 4 | 100% | 2018-02-02
|  |  | Total |  |  |  | 1672.5 | 1770 | 13.5625 | 226.8328 | 0.12815 | 2010.5 | 240.5 | 83.19%
88.04%
[7 empty] | 1672.5 | 1770 | 13.5625 | #REF! | #REF! | 2010.5 | 240.5